## Read Me
SD and Rent Maintenance Application - UAT Test Cases
Version 2.0.0-uat.1 (UAT Release 1)
Purpose | Manual user acceptance testing of the SD Maintenance screens and the new Rent Management module before production deployment.
Installer | SD-and-Rent-UAT-Setup-2.0.0-uat.1.exe. Install on one main PC ("This PC holds the data"), then on testers' PCs ("Connect to the main PC"). The UAT app is separate from the live SD Maintenance app; its data is test data only.
Emails | Dry-run: notification and password-reset emails are written to Administration > Email Log as "DryRun" and never sent.
How to test | 1. Work through the Test Cases sheet in order (later cases use data created by earlier ones). 2. Fill the yellow columns: Actual Result, Status, Severity (for Fail), Tested By, Test Date, Remarks. 3. For every Fail, describe the steps and attach a screenshot in Remarks or the shared folder. 4. Return the workbook; the Summary sheet updates automatically.
Status values | Pass - works as expected ¦ Fail - differs from the expected result ¦ Blocked - cannot be tested (e.g. depends on a failed case) ¦ Not Run - not yet tested
Severity (for Fail) | Critical - wrong amounts / data loss / cannot continue ¦ High - main function not working ¦ Medium - works with a workaround ¦ Low - cosmetic or wording
Enhancement ideas | Write them in Remarks with "Enhancement:" at the start, so they can be separated from bugs.
Dates and amounts | Dates are DD/MM/YYYY everywhere; amounts in Indian format (1,00,000.00).
Example of a filled row (format only)
Actual Result | Monthly amounts Rs 1,00,000 and Rs 52,000 shown; total Rs 1,52,000; saved
Status | Pass
Severity | (leave blank when Pass)
Tested By | Priya (Finance)
Test Date | 20/10/2026
Remarks | Enhancement: show the total in words as well

## Summary
UAT Summary - Version 2.0.0-uat.1
Counts update automatically from the Test Cases sheet.
Module | Total | Pass | Fail | Blocked | Not Run | % Complete
Installation
Login & Security
Masters
SD Master
SD Transaction
SD Reports
Rent Master
Rent Agreement
Rule Master
Waiver Master
Rent Schedule
SD & Rent Report
Total
Fails by severity
Critical
High
Medium
Low

## Test Cases
TC ID | Module | Screen | Scenario | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Tested By | Test Date | Remarks
INS-01 | Installation | Installer | Install the UAT app | Windows 10/11 64-bit PC; admin rights | 1. Run SD-and-Rent-UAT-Setup-2.0.0-uat.1.exe 2. If "Windows protected your PC" appears, click More info > Run anyway 3. Accept the default folder and finish | Installer file | App installs; "SD and Rent UAT" shortcut on Desktop and Start menu; app opens the "How is this PC used?" screen |  | Not Run
INS-02 | Installation | Setup screen | Set up the main (data) PC | App installed; first launch | 1. Choose "This PC holds the data" 2. Enter administrator email, password and confirm 3. Click Set up this PC | Admin email; password with 8+ characters, a letter and a number | Database is created in about a minute; login page opens; sign in as admin with the chosen password works |  | Not Run
INS-03 | Installation | Setup screen | Password rules on setup | First launch | 1. Choose "This PC holds the data" 2. Enter a 5-character password, then two different passwords | abc12; Test1234 / Test12345 | Clear messages: password needs 8+ characters with a letter and a number; "The two passwords do not match"; nothing is set up |  | Not Run
INS-04 | Installation | Settings | Find the address for other PCs | Main PC set up | On the main PC: Settings > Address for other PCs | - | Shows http://<IP>:5250 address(es) for other PCs |  | Not Run
INS-05 | Installation | Setup screen | Connect a second PC | Main PC running the app; same network | 1. Install on a second PC 2. Choose "Connect to the main PC" 3. Enter the main PC address, click Test connection, then Connect | e.g. 192.168.1.20 | Test connection reports success; the login page of the main PC opens; same data visible on both PCs |  | Not Run
INS-06 | Installation | Setup screen | Wrong main PC address | Second PC | Enter an address where the app is not running and click Connect | e.g. 192.168.1.250 | Message "No SD Maintenance server answered..."; app is not switched to that address |  | Not Run
INS-07 | Installation | File menu | Back up the database | Main PC | File > Back up database..., save the file | - | Backup file (.dump) is saved; "Backup complete" message |  | Not Run
INS-08 | Installation | Close | Closing the main PC app warns | Main PC | Close the app window | - | Confirmation that other PCs will lose access; Cancel keeps the app open |  | Not Run
SEC-01 | Login & Security | Login | Valid login | Admin user exists | Enter user name and password, click Sign in | admin / own password | Dashboard opens with "Good morning/afternoon, admin" and the menus |  | Not Run
SEC-02 | Login & Security | Login | Invalid password | - | Enter a wrong password | admin / wrong | "Invalid User Name or Password." shown; no login |  | Not Run
SEC-03 | Login & Security | Change Password | Change own password | Logged in | Administration > Change Password; enter current and new password twice | New password meeting the rules | Success message; next login works only with the new password |  | Not Run
SEC-04 | Login & Security | Forgot Password | Reset link email | Mail Server (SMTP) configured; UAT sends no real email (dry run) | Login page > Forgot password?; enter the user email | Registered email | Generic confirmation shown; Email Log lists the reset email as "DryRun" |  | Not Run
SEC-05 | Login & Security | Session | Idle timeout | Logged in | Leave the app idle for 30 minutes, then click a menu | - | Returned to the login page with an inactivity message |  | Not Run
SEC-06 | Login & Security | User Rights | Screen permissions | A non-admin user with View only on SD Master | Log in as that user and open SD Master | Test user | Screen opens read-only: no Add / Upload / Delete; menus without View rights are hidden |  | Not Run
MST-01 | Masters | Cost Center Master | Add / edit / delete a cost center | User has rights | 1. Add a cost center 2. Edit its name 3. Delete it | Name: UAT Test CC | Code auto-generated (CC0001...); changes saved with success message; delete removes it; duplicate name rejected |  | Not Run
MST-02 | Masters | Cost Center Master | Bulk upload | - | Download Template, fill 3 rows (one duplicate), Upload & Validate | Excel template | Valid rows saved; duplicate row reported Failed with a reason; report downloadable |  | Not Run
MST-03 | Masters | Location Master | Three-level hierarchy | - | Add Level 1, then Level 2 under it, then Level 3 under Level 2 | Region / City / Building | Each level saves; Level 2/3 dropdowns show only children of the chosen parent; names (no codes) shown |  | Not Run
MST-04 | Masters | User Master | Create a user and reset password | Admin | 1. Add user with email 2. Reset Password | uat.user1 / email | User created Active; reset sets a new password; user can log in |  | Not Run
MST-05 | Masters | User Rights Master | Grant rights incl. Rent screens | Admin; non-admin user exists | Select the user; tick View/Add/Edit/Delete/Upload for Rent Master and the new report; Save | - | Rights saved; that user now sees the Rent Transaction menu and the SD & Rent report |  | Not Run
MST-06 | Masters | Email Notification Master | Edit a template | Admin | Change trigger days, recipients and subject of Lease End Reminder; Save; check Preview | 30 days; uat@company.com | Saved; live preview shows the new subject with sample data |  | Not Run
MST-07 | Masters | Email Notification Master | Mail Server (SMTP) settings | Admin | Mail Server tab: enter SMTP host, port, user, password, sender; Test connection | Office SMTP details | Settings saved (password hidden); test reports success or a clear error |  | Not Run
SDM-01 | SD Master | SD Master | Add an SD record | Cost center and locations exist | Add SD Record; fill all mandatory fields; Save | Floor 3, Agreement Value 10,00,000; LCD/RCD/LED dates | SD Code auto-generated (SD000001...); record listed with amounts and dates DD/MM/YYYY |  | Not Run
SDM-02 | SD Master | SD Master | Validation messages | - | Save with LED before LCD and Agreement Value "abc" | - | All errors listed together; nothing saved |  | Not Run
SDM-03 | SD Master | SD Master | Duplicate Lease ID + Agreement No. + Floor | An SD exists | Add another SD with the same Lease ID, Agreement No. and Floor | - | Rejected: "already used by SD..." |  | Not Run
SDM-04 | SD Master | SD Master | Multi-select filters and date preset | Several SD records | Filter by two cost centers and two Level 1 locations; set Lease End to "This Financial Year" | - | Only matching records listed; Clear resets; Export to Excel gives the same rows |  | Not Run
SDM-05 | SD Master | SD Master | Passive status notification | Template enabled | Edit an SD and set Landlord Status to Passive | - | Status history row added; Email Log shows the Passive alert (DryRun) |  | Not Run
SDM-06 | SD Master | SD Master | Bulk upload new and update rows | - | Template with 2 new rows and 1 row with an existing SD Code changing only Floor | - | New SD Codes created; existing record updated, blank cells keep their values |  | Not Run
SDT-01 | SD Transaction | SD Transaction | Add SD Paid | SD record with Agreement Value 10,00,000 | Select the SD Code; Add Transaction: SD Paid 6,00,000 | FY 2026-2027 | Saved; SD Balance 4,00,000 and Repayable 6,00,000 shown in the sticky SD header |  | Not Run
SDT-02 | SD Transaction | SD Transaction | Paid above Agreement Value blocked | As above | Add SD Paid 5,00,000 more | - | Rejected: total SD Paid cannot exceed Agreement Value |  | Not Run
SDT-03 | SD Transaction | SD Transaction | Refund / Transfer / Adjustment | Paid 6,00,000 | Add Refund 1,00,000, then Transfer 50,000 | - | Repayable reduces to 4,50,000; a refund larger than Repayable is rejected |  | Not Run
SDT-04 | SD Transaction | SD Transaction | Passive SD blocked | SD with Passive status | Try to add a transaction | - | Add Transaction disabled with an explanation |  | Not Run
SDT-05 | SD Transaction | SD Transaction | Bulk upload transactions | - | Template with valid rows and one row over the Agreement Value | - | Valid rows saved; over-limit row Failed with the reason |  | Not Run
SDR-01 | SD Reports | SD Balance Report | Totals and export | Transactions exist | Open the report; filter by cost center; Export to Excel | - | Per-SD balances; totals row matches; export contains the same rows |  | Not Run
SDR-02 | SD Reports | SD Dashboard | KPIs, alerts and charts | Data exists | Open Reports > SD Dashboard; change filters; drill into a Level 1 location bar | - | KPI cards, upcoming lease alerts (red/orange/green), charts and tables update with filters; drill-down shows Level 2 |  | Not Run
SDR-03 | SD Reports | SD Dashboard | Quick actions and exports | - | Use Add SD Master, Export to Excel and Export to PDF | - | Add form opens on SD Master; Excel has one sheet per section; print dialog offers Save as PDF |  | Not Run
SDR-04 | SD Reports | Email Log / Audit Log | Audit trail | Changes made above | Open Audit Log; filter by record type "SD Master" | - | Each add/edit/delete/upload listed with user, time and old/new values |  | Not Run
RMS-01 | Rent Master | Rent Master | Create a Rent Code | SD record with LCD, RCD and LED | Rent Transaction > Rent Master > Add Rent Code; pick the SD Code; enter Landlord Name; Save | Landlord: Venkat | Rent Code RENT0001 generated; Cost Center, Floor, LCD, RCD, LED shown read-only from SD Master |  | Not Run
RMS-02 | Rent Master | Rent Master | Duplicate Business Key | RENT0001 exists | Add again with the same SD Code and Landlord Name (different case) | venkat | Rejected: Rent Code already exists for this Cost Center, SD Code, Floor and Landlord Name |  | Not Run
RMS-03 | Rent Master | Rent Master | SD without RCD / LED | SD record without RCD or LED | Try to create a Rent Code for it | - | Rejected: update RCD / LED in SD Master first |  | Not Run
RMS-04 | Rent Master | Rent Master | Inactive with end date | Rent Code with generated schedule | Edit: LL Status = Inactive; enter Inactive End Date mid-month | 15/08/2027 | Inactive End Date is mandatory; schedule stops after that date; that month pro-rated |  | Not Run
RMS-05 | Rent Master | Rent Master | Bulk upload | - | Template: 1 valid row, 1 row with a Floor that does not match SD Master, 1 duplicate | - | Result file: Success (green) / Rejected (red) with Remark for each row |  | Not Run
RAG-01 | Rent Agreement | Rent Agreement Master | Add agreement with components | Rent Code exists | Add Agreement; Individual; Office Rent 10000 Sq.Ft x 50 x 20%; Maintenance 40000 x 13 x 10%; Save | As given | Monthly amounts Rs 1,00,000 and Rs 52,000, total Rs 1,52,000 shown live; saved |  | Not Run
RAG-02 | Rent Agreement | Rent Agreement Master | Conditional mandatory fields | - | Enter Office Rent Sq.Ft only and Save | 1000 | Errors: Rate and % required once Sq.Ft is entered |  | Not Run
RAG-03 | Rent Agreement | Rent Agreement Master | Signage / Solar (Rate per month) | - | Signage Rate / Month 30,00,000 with 20% | - | Monthly amount Rs 6,00,000 (no Sq.Ft needed) |  | Not Run
RAG-04 | Rent Agreement | Rent Agreement Master | One active agreement per Rent Code + status | Active Individual agreement exists | Add a second Active Individual agreement for the same Rent Code | - | Rejected; make the first Inactive first |  | Not Run
RAG-05 | Rent Agreement | Rent Agreement Master | Locked once used | A rule exists for the Rent Code | Edit the agreement amounts; try Delete | - | Only Status / Remark editable; delete blocked with a message |  | Not Run
RAG-06 | Rent Agreement | Rent Agreement Master | Transfer to a new landlord | Second Rent Code on the same SD Code | Add Agreement on the new Rent Code: Transfer, Transfer From = old Rent Code, Effective Date; leave components blank | 01/11/2026 | Components, rules and later waivers copied; old Rent Code rent stops the day before; new one starts on the date |  | Not Run
RAG-07 | Rent Agreement | Rent Agreement Master | Bulk upload / update | - | Template rows for new agreements and an update of an existing Rent Code + status | - | Result file with Success / Rejected and Remark |  | Not Run
RUL-01 | Rule Master | Rule Master | RCD escalation rule | Active agreement | Add Rule: RCD, Escalation Month 12, 5% | RCD 15/01/2026 | Escalation date 15/01/2027 shown; schedule increases 5% from that date (mid-month pro-rated) |  | Not Run
RUL-02 | Rule Master | Rule Master | Second rule chains | One RCD rule | Add another RCD rule, 12 months, 5% | - | Escalates 12 months after the previous escalation; compounding (1,05,000 -> 1,10,250) |  | Not Run
RUL-03 | Rule Master | Rule Master | LED limit and LCD/RCD mixing | RCD rule exists | Add a rule escalating after the LED; add an LCD rule | - | Both rejected with clear messages |  | Not Run
RUL-04 | Rule Master | Rule Master | Negative / zero percentage | - | Add rules with -10% and 0% | - | Accepted; -10% reduces rent, 0% keeps it |  | Not Run
RUL-05 | Rule Master | Rule Master | Normal Day rule | - | Rule Type Normal Day, From / To dates, 10% | 01/06/2026 - 30/06/2026 | Rent +10% only for those days |  | Not Run
RUL-06 | Rule Master | Rule Master | Applies to several components | - | Applies to: tick Office Rent and Cafe only | - | Only those components escalate; list shows the selected components |  | Not Run
RUL-07 | Rule Master | Rule Master | Bulk upload with Yes/No columns | - | Template: Applies to: Office Rent = Yes, others No; one row with all blank; one with "Maybe" | - | Yes rows apply to selected components; all blank = all components; "Maybe" rejected |  | Not Run
WAV-01 | Waiver Master | Waiver Master | Rent-free period | Active agreement | Add Waiver 01/01/2027 - 31/03/2027, Status Yes | - | Jan-Mar 2027 rent becomes Rs 0 in the schedule |  | Not Run
WAV-02 | Waiver Master | Waiver Master | Overlap and range checks | Waiver exists | Add an overlapping waiver; a waiver ending after LED; From after To | - | All rejected with messages |  | Not Run
WAV-03 | Waiver Master | Waiver Master | Switch a waiver off | Waiver Yes exists | Edit and set Waiver Status = No | - | Normal rent returns for that period after regeneration |  | Not Run
WAV-04 | Waiver Master | Waiver Master | Waiver on selected components | - | Applies to: Maintenance Charges only | - | Only Maintenance becomes Rs 0; rent components still charged |  | Not Run
WAV-05 | Waiver Master | Waiver Master | Bulk upload | - | Template with Yes/No Applies to columns; one row matching an existing waiver with Status No | - | Existing waiver updated to No; results file Success / Rejected |  | Not Run
RSC-01 | Rent Schedule | Rent Schedule | Generate schedule | Agreement, rule and waiver set up | Choose the period (e.g. This Financial Year); Generate / Regenerate | - | Month-wise lines per component; Maintenance from LCD, rent from RCD, ending at LED |  | Not Run
RSC-02 | Rent Schedule | Rent Schedule | Worked example (scope 6.4) | LCD 01/01/2026, RCD 01/04/2026, LED 01/12/2026; 1000 x 10 x 10%; RCD rule 1 month 15%; waiver 01/10-30/10/2026 | Generate 2026 | - | Apr Rs 1,000; May-Sep Rs 1,150; Oct Rs 37.10 (31 Oct charged); Nov Rs 1,150; Dec Rs 37.10 |  | Not Run
RSC-03 | Rent Schedule | Rent Schedule | Automatic regeneration | Schedule generated | Change a waiver or rule, then reopen Rent Schedule | - | Future months recalculated automatically; generation history shows "Auto: ..." |  | Not Run
RSC-04 | Rent Schedule | Rent Schedule | Missing dates message | Rent Code whose SD lost its LED | Generate | - | Message lists the Rent Code: LED is missing; others still generate |  | Not Run
RSC-05 | Rent Schedule | Rent Schedule | Filters, summaries and export | Schedule generated | Filter by landlord and Agreement Header; switch to By Cost Center; Export to Excel and PDF | - | Totals match filters; summary views add up; Excel has lines and By Agreement Header sheet |  | Not Run
SRR-01 | SD & Rent Report | SD & Rent Transaction Summary | Combined list | SD transactions and a generated schedule exist | Reports > SD & Rent Transaction Summary; period This Financial Year | - | SD rows (Security Deposit) and Rent / Maintenance rows together with Cost Center, SD Code, Landlord, Floor, Rent Code, Expense Head, Effective Date, amount, Status |  | Not Run
SRR-02 | SD & Rent Report | SD & Rent Transaction Summary | Filters | - | Filter by Cost Center, Landlord, Floor, SD Code and Expense Head (several values) | - | Only matching rows; totals tiles update |  | Not Run
SRR-03 | SD & Rent Report | SD & Rent Transaction Summary | Summaries and export | - | Views By Cost Center / Landlord / Expense Head; Export to Excel | - | Summary totals equal the grand total; Excel has the list plus summary sheets |  | Not Run